## TASKS
TASK LIST
ID | Column1 | START DATE | DUE DATE | State | % COMPLETE | DONE | Comment
2748 | as a customer I want to be shown a welcome screen when I try to access the application so that I know I am on the parking permit application | 2020-08-21 | Date | Done | 100% | 1
2761 | as a Customer I want to request a new parking permit starting on a specific date, for a specified period, in a specific parking space so that I can park my car legally |  | Date | In progress | 25% | 0
2853 | as a customer i want to add my vehicle details so that I am able to park these vehicles in the parking slots |  | Date | Not Started | 0% | 0
3431 | as a Admin I want to see the area's available to me and hide any areas that should not be available. |  |  |  | 0% | 0
3434 | As an Administrator: Validation on parking spaces - New / Edit |  |  |  | 0% | 0
3438 | as a User i want to have the standard logon options available (logon, logout, change password, forgot password) so that I can logon, logout, change password, recover from forgetting password as necessary |  |  |  | 0% | 0
3439 | as a Customer I want to see the menu options available to me so that I can find the correct area of the application to perform the actions I want |  |  |  | 0% | 0
3440 | as a Customer i want to see my existing parking permits so that I know what parking permits I have |  |  |  | 0% | 0
3441 | as a User I want to see my account information so that I can see the details are correct |  |  |  | 0% | 0
3442 | as a User i want to edit my account information so that the information is correct |  |  |  | 0% | 0
3443 | as a Customer i want to view my vehicles so that I can see the details are correct |  |  |  | 0% | 0
3444 | as a Customer i want to edit my vehicle details so that my vehicle details are correct |  |  |  | 0% | 0
3446 | as a Administrator i want to see the menu options available to me so that I can find the correct area of the application to perform the actions I want |  |  |  | 0% | 0
3447 | as an Administrator i want to add new parking fee so that the correct fee can be charged |  |  |  | 0% | 0
3448 | as an Administrator i want to view all parking fees so that I can see what is currently being charged |  |  |  | 0% | 0
3449 | as an Administrator i want to edit a parking fee so that the correct fee can be charged for the correct permit type |  |  |  | 0% | 0
3450 | as an Administrator i want to add a new parking space so that new parking spaces can be made available to customers |  |  |  | 0% | 0
3451 | as an Administrator i want to view all parking spaces so that I can see all the spaces |  |  |  | 0% | 0
3452 | as an Administrator i want to edit a parking space so that the correct parking spaces are available to customers |  |  |  | 0% | 0
3541 | Delete Parking Fee |  |  |  | 0% | 0
3542 | Delete Parking Space |  |  |  | 0% | 0

## Sheet1
ID | Title | State
2748 | as a customer I want to be shown a welcome screen when I try to access the application so that I know I am on the parking permit application | Jasmine Needed
2761 | as a Customer I want to request a new parking permit starting on a specific date, for a specified period, in a specific parking space so that I can park my car legally | Jasmine Needed
2853 | as a customer i want to add my vehicle details so that I am able to park these vehicles in the parking slots | Jasmine Needed
3431 | as a Admin I want to see the area's available to me and hide any areas that should not be available. | Jasmine Needed
3434 | As an Administrator: Validation on parking spaces - New / Edit | Jasmine Needed
3438 | as a User i want to have the standard logon options available (logon, logout, change password, forgot password) so that I can logon, logout, change password, recover from forgetting password as necessary | Jasmine Needed
3439 | as a Customer I want to see the menu options available to me so that I can find the correct area of the application to perform the actions I want | Jasmine Needed
3440 | as a Customer i want to see my existing parking permits so that I know what parking permits I have | Jasmine Needed
3441 | as a User I want to see my account information so that I can see the details are correct | Jasmine Needed
3442 | as a User i want to edit my account information so that the information is correct | Jasmine Needed
3443 | as a Customer i want to view my vehicles so that I can see the details are correct | Jasmine Needed
3444 | as a Customer i want to edit my vehicle details so that my vehicle details are correct | Jasmine Needed
3446 | as a Administrator i want to see the menu options available to me so that I can find the correct area of the application to perform the actions I want | Jasmine Needed
3447 | as an Administrator i want to add new parking fee so that the correct fee can be charged | Jasmine Needed
3448 | as an Administrator i want to view all parking fees so that I can see what is currently being charged | Jasmine Needed
3449 | as an Administrator i want to edit a parking fee so that the correct fee can be charged for the correct permit type | Jasmine Needed
3450 | as an Administrator i want to add a new parking space so that new parking spaces can be made available to customers | Jasmine Needed
3451 | as an Administrator i want to view all parking spaces so that I can see all the spaces | Jasmine Needed
3452 | as an Administrator i want to edit a parking space so that the correct parking spaces are available to customers | Jasmine Needed
3541 | Delete Parking Fee | Jasmine Needed
3542 | Delete Parking Space | Jasmine Needed